## Summary
Sprint Backlog Summary
Auto-reconciled with Project Budget · Total target: 1,236 hours
Sprint | Planning Mode | Tasks | Hours Planned | % of Budget
Sprint 1 | Detailed | 16 | 164 | 13.27%
Sprint 2 | Detailed | 17 | 224 | 18.12%
Sprint 3 | Detailed | 18 | 278 | 22.49%
Sprint 4 | High-level (rolling wave) | 12 | 186 | 15.05%
Sprint 5 | High-level (rolling wave) | 9 | 146 | 11.81%
Total |  | 72 | 998 | 80.74%
Budget target |  |  | 1236
Variance |  |  | -238

## Backlog
COMP47360 Research Practicum — Sprint Backlog
Sprint 1
Epic | Task | Estimated Hours | Real Hours | Completion Date | Nancy | Hansel | Alison | Eoin | Sean | Status | Budget Category
PM | Personas & interviews | 16 | 16 | 2026-05-25 | TRUE | TRUE | TRUE | TRUE | TRUE | Completed | 1. Requirements & Research
PM | Research competitors | 8 | 6 | 2026-05-25 | TRUE | TRUE | TRUE | TRUE | TRUE | Completed | 1. Requirements & Research
PM | Develop early prototypes & mockups | 12 | 12 | 2026-05-28 | TRUE | TRUE | TRUE | TRUE | TRUE | Completed | 2. Design (UX/UI)
Infra | Select technologies | 8 | 5 | 2026-05-29 |  | TRUE | TRUE | TRUE | TRUE | Completed | 3. Backend Development
PM | Define user stories & acceptance criteria | 16 | 16 | 2026-06-02 | TRUE |  |  |  |  | Completed | 10. Project Management
PM | Create budget | 10 | 8 | 2026-05-29 | TRUE |  |  |  |  | Completed | 10. Project Management
Infra | Create GitHub Repository | 4 | 5 | 2026-05-26 |  | TRUE |  |  |  | Completed | 9. Deployment & DevOps
Infra | Define Git workflow | 6 | 4 | 2026-05-26 |  | TRUE |  |  |  | Completed | 9. Deployment & DevOps
ML / Data | Crowd data feasibility spike (NYC Open Data) | 24 | 24 | 2026-06-05 |  |  | TRUE |  |  | Completed | 6. ML / Data Engineering
Infra | React-Vite + TypeScript env | 12 | 12 | 2026-05-25 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Infra | Mobile env | 12 | 10 | 2026-06-05 |  |  |  |  | TRUE | Completed | 5. Mobile Development
Auth | Initial frontend structure (no features) | 8 | 8 | 2026-06-04 |  |  |  | TRUE | TRUE | Completed | 4. Web Frontend
Infra | Initialise FastAPI backend env | 12 | 12 | 2026-06-02 |  | TRUE |  |  |  | Completed | 3. Backend Development
PM | UX strategy (web vs mobile differentiation) | 16 | 26 | 2026-06-03 | TRUE |  |  |  | TRUE | Completed | 2. Design (UX/UI)
| Sprint 1 Total | 164 | 164
Sprint 2
Epic | Task | Estimated Hours | Real Hours | Completion Date | Nancy | Hansel | Alison | Eoin | Sean | Status | Budget Category
Auth | Auth API setup (Firebase) | 16 | 16 | 2026-06-12 |  | TRUE |  |  |  | Completed | 3. Backend Development
Auth | Auth flow UI (Web) | 12 | 12 | 2026-06-16 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Auth | Bottom navigation component (Web) | 8 | 8 | 2026-06-16 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Auth | Auth flow + Nav (Mobile) | 16 | 16 | 2026-06-16 |  |  |  |  | TRUE | Completed | 5. Mobile Development
Explore | POI database schema + initial 30 POIs | 20 | 20 | 2026-06-23 |  | TRUE |  |  |  | Completed | 3. Backend Development
Explore | GET /pois + GET /poi/{id} endpoints | 12 | 12 | 2026-06-16 |  | TRUE |  |  |  | Completed | 3. Backend Development
Explore | POI popularity flag + Save/Unsave POI API endpoints | 4 | 4 | 2026-06-19 |  | TRUE |  |  |  | Completed | 3. Backend Development
Explore | Explore tab UI + Save icon on POI cards (Web) | 16 | 16 | 2026-06-17 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Explore | POI Detail page UI (Web) | 16 | 16 | 2026-06-17 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Explore | Explore tab + POI Detail (Mobile) | 28 | 24 | 2026-06-30 |  |  |  |  | TRUE | Completed | 5. Mobile Development
ML / Data | Provide data quality report | 16 | 16 | 2026-06-17 |  |  | TRUE |  |  | Completed | 6. ML / Data Engineering
ML / Data | Provide peliminary integrated dataset | 24 | 24 | 2026-06-18 |  |  | TRUE |  |  | Completed | 6. ML / Data Engineering
My Itinerary | My Itinerary tab shell + date picker (Web) | 8 | 8 | 2026-06-19 |  |  |  | TRUE |  | Completed | 4. Web Frontend
My Itinerary | My Itinerary tab shell + date picker (Mobile) | 6 | 6 | 2026-06-30 |  |  |  |  | TRUE | Completed | 5. Mobile Development
PM | Sprint 2 ceremonies + retro | 6 | 6 | 2026-06-19 | TRUE |  |  |  |  | Completed | 10. Project Management
PM | Mid-fidelity wireframes (AI-accelerated, 4 core screens) | 16 | 16 | 2026-06-16 | TRUE |  |  |  |  | Completed | 2. Design (UX/UI)
AI Planner | AI Planner Spike — API + session memory POC | 6 | 6 | 2026-06-25 | TRUE |  |  |  |  | Completed | 6. ML / Data Engineering
| Sprint 2 Total | 224 | 226
Sprint 3
Epic | Task | Estimated Hours | Real Hours | Completion Date | Nancy | Hansel | Alison | Eoin | Sean | Status | Budget Category
Explore | Map POIs to nearest subway station | 6 | 6 | 2026-07-02 |  | TRUE |  |  |  | Completed | 3. Backend Development
Explore | Fallback msg: Crowd Forecast (no POI data) | 4 | 4 | 2026-07-03 |  | TRUE |  | TRUE | TRUE | Completed | 4. Web Frontend
Explore | POI database schema + initial 30 POIs [Carryover] | 20 | 20 | 2026-06-25 |  | TRUE |  |  |  | Completed | 3. Backend Development
Explore | Crowd Forecast chart UI (Web) | 8 | 8 | 2026-06-25 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Explore | Crowd Forecast chart UI (Mobile) | 8 | 8 | 2026-06-30 |  |  |  |  | TRUE | Completed | 5. Mobile Development
ML / Data | Finalised busyness formula and result grade | 12 | 12 | 2026-06-25 |  |  | TRUE |  |  | Completed | 6. ML / Data Engineering
ML / Data | ML preparation: Training plan, initial result | 20 | 20 | 2026-07-01 |  |  | TRUE |  |  | Completed | 6. ML / Data Engineering
My Itinerary | Itinerary generation core engine (Rule-based & AI core scheduling logic) | 20 | 20 | 2026-07-01 |  | TRUE |  |  |  | Completed | 6. ML / Data Engineering
My Itinerary | Crowd data integration + Itinerary Generation & Update API endpoints | 16 | 16 | 2026-07-01 |  | TRUE |  |  |  | Completed | 6. ML / Data Engineering
My Itinerary | 5 POI/day + geographic proximity allocation algorithm | 12 | 28 | 2026-07-07 |  | TRUE |  |  |  | Completed | 6. ML / Data Engineering
My Itinerary | My Itinerary 4-section UI (Search/Selected/Saved/Popular) — Web | 20 | 20 | 2026-07-01 |  |  |  | TRUE |  | Completed | 4. Web Frontend
My Itinerary | Itinerary view page (scheduled output) — Web | 16 | 16 | 2026-07-01 |  |  |  | TRUE |  | Completed | 4. Web Frontend
My Itinerary | "Why this time" UI integration (Web) | 6 | 6 | 2026-06-26 |  |  |  | TRUE |  | Completed | 4. Web Frontend
My Itinerary | Loading & error states (Web) | 6 | 6 | 2026-06-26 |  |  |  | TRUE |  | Completed | 4. Web Frontend
My Itinerary | Itinerary view (Infinite scroll scheduled output) — Mobile | 24 | 6 | 2026-06-26 |  |  |  |  | TRUE | Completed | 5. Mobile Development
My Itinerary | "Why this time" + states (Mobile) | 16 | 6 | 2026-06-26 |  |  |  |  | TRUE | Completed | 5. Mobile Development
My Itinerary | Itinerary Editor (Dropdown Pill time-change & Hover-remove) — Web | 12 | 12 | 2026-06-26 |  |  |  | TRUE |  | In Progress | 4. Web Frontend
My Itinerary | My Itinerary 4-section UI (Mobile) | 20 | 6 | 2026-06-26 |  |  |  |  | TRUE | Completed | 5. Mobile Development
My Itinerary | Fallback msg: "Why this time" (no ML data) | 6 | 6 | 2026-06-26 |  | TRUE |  | TRUE | TRUE | Completed | 4. Web Frontend
PM | High-fi mockups (AI-accelerated, core flow) | 10 | 10 | 2026-07-01 | TRUE |  |  |  |  | Completed | 2. Design (UX/UI)
PM | Polish edge cases + empty states | 6 | 6 | 2026-07-01 | TRUE |  |  |  |  | Completed | 4. Web Frontend
PM | User testing prep | 4 | 4 | 2026-07-03 | TRUE |  |  |  |  | Completed | 8. Testing & QA
PM | Sprint 3 ceremonies + retro | 6 | 6 | 2026-07-03 | TRUE |  |  |  |  | Completed | 10. Project Management
| Sprint 3 Total | 278 | 252
Sprint 4
| Task | Estimated Hours | Real Hours | Completion Date | Nancy | Hansel | Alison | Eoin | Sean | Status | Budget Category
Explore | Filter POIs by interest / accessibility | 16 | 16 | 2026-07-11 |  |  |  | TRUE | TRUE | Completed | 4. Web Frontend
Profile | Profile tab (Web) | 4 | 4 | 2026-07-13 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Profile | Profile tab (Mobile) | 4 | 4 | 2026-07-08 |  |  |  |  | TRUE | Completed | 5. Mobile Development
AI Planner | AI Planner backend (Gemini + session memory) | 16 | 16 | 2026-07-13 |  | TRUE |  |  |  | Completed | 6. ML / Data Engineering
AI Planner | AI Planner UI (Web) | 12 | 12 | 2026-07-13 |  |  |  | TRUE |  | Completed | 4. Web Frontend
AI Planner | AI Planner UI (Mobile) | 12 | 12 | 2026-07-14 |  |  |  |  | TRUE | Completed | 5. Mobile Development
Infra | Deployment | 12 | 12 | 2026-07-13 |  |  | TRUE |  |  | Completed | 9. Deployment & DevOps
Infra | Database setup (PostGIS) | 16 | 16 | 2026-07-15 |  | TRUE |  |  |  | Completed | 3. Backend Development
ML / Data | Evaluate ML model (metrics, validation) | 12 | 12 | 2026-07-16 |  |  | TRUE |  |  | Completed | 6. ML / Data Engineering
ML / Data | Integrate ML predictions with backend | 12 | 12 | 2026-07-15 |  | TRUE | TRUE |  |  | Completed | 6. ML / Data Engineering
My Itinerary | In-line Itinerary Editor — Mobile | 6 | 6 | 2026-07-17 |  |  |  |  | TRUE | Completed | 5. Mobile Development
Saved | Saved tab functional (Web) | 8 | 8 | 2026-07-08 |  |  |  | TRUE |  | Completed | 4. Web Frontend
Saved | Saved tab functional (Mobile) | 8 | 8 | 2026-07-08 |  |  |  |  | TRUE | Completed | 5. Mobile Development
PM | UAT Test | 30 | 30 | 2026-07-11 | TRUE |  |  |  |  | Completed | 8. Testing & QA
PM | Unit Test | 16 | 16 | 2026-07-13 | TRUE |  |  |  |  | Completed | 8. Testing & QA
PM | Literature review | 20 | 20 | 2026-07-08 | TRUE |  |  |  |  | Completed | 1. Requirements & Research
PM | Sprint 4 ceremonies + retro | 6 | 6 | 2026-07-14 | TRUE |  |  |  |  | Completed | 10. Project Management
| Sprint 4 Total | 186 | 210
Sprint 5
| Task | Estimated Hours | Real Hours | Completion Date | Nancy | Hansel | Alison | Eoin | Sean | Status | Budget Category
Infra | Performance optimization | 16 | 16 | 2026-07-21 | TRUE | TRUE | TRUE | TRUE | TRUE | Completed | 3. Backend Development
PM | Final user testing + iterations | 24 | 24 | 2026-07-27 | TRUE |  |  |  |  | Completed | 8. Testing & QA
PM | Demo preparation + rehearsal | 16 | 16 | 2026-07-26 | TRUE |  | TRUE | TRUE | TRUE | Completed | 10. Project Management
PM | Final paper writing | 60 | 60 | 2026-07-31 | TRUE | TRUE | TRUE | TRUE | TRUE | Completed | 10. Project Management
PM | Documentation cleanup | 12 | 12 | 2026-07-28 | TRUE | TRUE | TRUE | TRUE | TRUE | Completed | 10. Project Management
Infra | Final deployment + monitoring | 12 | 12 | 2026-07-27 |  |  | TRUE |  |  | Completed | 9. Deployment & DevOps
PM | Sprint 5 ceremonies + final retro | 6 | 6 | 2026-07-31 | TRUE |  |  |  |  | Completed | 10. Project Management
| Sprint 5 Total | 146 | 146

## Burndown chart
Sprint 1 Burndown Chart
Sprint 1: 25 May - 05 Jun 2026 · Total planned: 204h · Working days: 10
Day | Date | Story point | Done Today | Cumulative Done | Actual Remaining
0 | 2026-05-24 | 40 | 0 | 0 | 40
1 | 2026-05-25 | 36 | 8 | 8 | 32
2 | 2026-05-26 | 32 | 3 | 11 | 29
3 | 2026-05-27 | 28 | 0 | 11 | 29
4 | 2026-05-28 | 24 | 3 | 14 | 26
5 | 2026-05-29 | 20 | 4 | 18 | 22
6 | 2026-06-01 | 16 | 0 | 18 | 22
7 | 2026-06-02 | 12 | 5 | 23 | 17
8 | 2026-06-03 | 8 | 6 | 29 | 11
9 | 2026-06-04 | 4 | 2 | 31 | 9
10 | 2026-06-05 | 0 | 9 | 40 | 0
Summary
Total Story point | 40
Total Completed | 40
Remaining | 0
Completion % | 100%
Sprint 2 Burndown Chart
Sprint 1: 08 Jun 2026 - 19 Jun 2026
Day | Date | Story point | Done Today | Cumulative Done | Actual Remaining
0 | 2026-06-07 | 44 | 0 | 0 | 44
1 | 2026-06-08 | 39.6 |  | 0 | 44
2 | 2026-06-09 | 32 |  | 0 | 44
3 | 2026-06-10 | 28 |  | 0 | 44
4 | 2026-06-11 | 24 |  | 0 | 44
5 | 2026-06-12 | 20 | 3 | 3 | 41
6 | 2026-06-15 | 16 |  | 3 | 41
7 | 2026-06-16 | 12 | 12 | 15 | 29
8 | 2026-06-17 | 8 | 9 | 24 | 20
9 | 2026-06-18 | 4 | 5 | 29 | 15
10 | 2026-06-19 | 0 | 4 | 33 | 11
Summary
Total Story point | 44
Total Completed | 33
Remaining | 11
Completion % | 75%
Sprint 3 Burndown Chart
Sprint 1: 22 Jun 2026 - 3 July 2026
Day | Date | Story point | Done Today | Cumulative Done | Actual Remaining
0 | 2026-06-21 | 57 | 0 | 0 | 57
1 | 2026-06-22 | 51.3 |  | 0 | 57
2 | 2026-06-23 | 45.6 |  | 0 | 57
3 | 2026-06-24 | 39.9 |  | 0 | 57
4 | 2026-06-25 | 34.2 | 8 | 8 | 49
5 | 2026-06-26 | 28.5 | 2 | 10 | 47
6 | 2026-06-29 | 22.8 |  | 10 | 47
7 | 2026-06-30 | 17.1 | 2 | 12 | 45
8 | 2026-07-01 | 11.4 | 17 | 29 | 28
9 | 2026-07-02 | 5.7 |  | 29 | 28
10 | 2026-07-03 | 0 | 10 | 39 | 18
Summary
Total Story point | 57
Total Completed | 39
Remaining | 18
Completion % | 68.42%
Sprint 4 Burndown Chart
Sprint 4: 6 Jul 2026 - 17 Jul 2026
Day | Date | Story point | Done Today | Cumulative Done | Actual Remaining
0 | 2026-07-05 | 43 | 0 | 0 | 43
1 | 2026-07-06 | 38.7 | 0 | 0 | 43
2 | 2026-07-07 | 34.4 | 0 | 0 | 43
3 | 2026-07-08 | 30.1 | 5 | 5 | 38
4 | 2026-07-09 | 25.8 | 4 | 9 | 34
5 | 2026-07-10 | 21.5 | 4 | 13 | 30
6 | 2026-07-13 | 17.2 | 8 | 21 | 22
7 | 2026-07-14 | 12.9 | 6 | 27 | 16
8 | 2026-07-15 | 8.6 | 6 | 33 | 10
9 | 2026-07-16 | 4.3 | 4 | 37 | 6
10 | 2026-07-17 | 0 | 6 | 43 | 0
Summary
Total Story point | 43
Total Completed | 43
Remaining | 0
Completion % | 100%
Sprint 5 Burndown Chart
Sprint 5: 20 Jul 2026 - 31 Jul 2026
Day | Date | Story point | Done Today | Cumulative Done | Actual Remaining
0 | 2026-07-19 | 19 | 0 | 0 | 19
1 | 2026-07-20 | 17.1 | 0 | 0 | 19
2 | 2026-07-21 | 15.2 | 3 | 3 | 16
3 | 2026-07-22 | 13.3 | 4 | 7 | 12
4 | 2026-07-23 | 11.4 | 2 | 9 | 10
5 | 2026-07-24 | 9.5 | 2 | 11 | 8
6 | 2026-07-27 | 7.6 | 2 | 13 | 6
7 | 2026-07-28 | 5.7 | 2 | 15 | 4
8 | 2026-07-29 | 3.8 | 2 | 17 | 2
9 | 2026-07-30 | 1.9 | 1 | 18 | 1
10 | 2026-07-31 | 0 | 1 | 19 | 0
Summary
Total Story point | 19
Total Completed | 19
Remaining | 0
Completion % | 100%

## Timeline
Gantt Chart
[5 empty] | Kickoff | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Submit
Person | Task | Sprint | Est.h | Status (see Backlog) | W1 18 May | W2 25 May | W3 1 Jun | W4 8 Jun | W5 15 Jun | W6 22 Jun | W7 29 Jun | W8 6 Jul | W9 13 Jul | W10 20 Jul | W11 27 Jul | W12 3 Aug
Nancy
Nancy | Personas & interviews | Sprint 1 | 16 |  |  | ● | ●
Nancy | Research competitors | Sprint 1 | 8 |  |  | ● | ●
Nancy | Develop early prototypes & mockups | Sprint 1 | 12 |  |  | ● | ●
Nancy | Define user stories & acceptance criteria | Sprint 1 | 16 |  |  | ● | ●
Nancy | Create budget | Sprint 1 | 10 |  |  | ● | ●
Nancy | UX strategy (web vs mobile differentiation) | Sprint 1 | 16 |  |  | ● | ●
Nancy | Mid-fidelity wireframes (4 core screens) | Sprint 2 | 16 |  |  |  |  | ● | ●
Nancy | Sprint 2 ceremonies + retro | Sprint 2 | 6 |  |  |  |  | ● | ●
Nancy | High-fi mockups (AI-accelerated, core flow) | Sprint 3 | 10 | [6 empty] | ● | ●
Nancy | Polish edge cases + empty states | Sprint 3 | 6 | [6 empty] | ● | ●
Nancy | User testing prep + recruitment | Sprint 3 | 4 | [6 empty] | ● | ●
Nancy | Sprint 3 ceremonies + retro | Sprint 3 | 6 | [6 empty] | ● | ●
Nancy | A/B testing setup + 1 design test | Sprint 4 | 10 | [8 empty] | ● | ●
Nancy | User testing sessions (target users) | Sprint 4 | 16 | [8 empty] | ● | ●
Nancy | Literature review (parallel, continuous) | Sprint 4 | 20 | [8 empty] | ● | ●
Nancy | Sprint 4 ceremonies + retro | Sprint 4 | 6 | [8 empty] | ● | ●
Nancy | Demo preparation + rehearsal | Sprint 5 | 16 | [10 empty] | ● | ●
Nancy | Final paper writing | Sprint 5 | 40 | [10 empty] | ● | ●
Nancy | Documentation cleanup | Sprint 5 | 12 | [10 empty] | ● | ●
Nancy | Sprint 5 ceremonies + final retro | Sprint 5 | 6 | [10 empty] | ● | ●
Hansel
Hansel | Select technologies | Sprint 1 | 8 |  |  | ● | ●
Hansel | Create GitHub Repository | Sprint 1 | 4 |  |  | ● | ●
Hansel | Define Git workflow | Sprint 1 | 6 |  |  | ● | ●
Hansel | Initialise FastAPI backend env | Sprint 1 | 12 |  |  | ● | ●
Hansel | Auth API setup (Firebase) | Sprint 2 | 16 |  |  |  |  | ● | ●
Hansel | POI database schema + initial 30 POIs | Sprint 2 | 20 |  |  |  |  | ● | ●
Hansel | GET /pois + GET /poi/{id} endpoints | Sprint 2 | 12 |  |  |  |  | ● | ●
Hansel | POI popularity flag + Save/Unsave POI API | Sprint 2 | 4 |  |  |  |  | ● | ●
Hansel | AI Planner Spike — API + session memory POC | Sprint 2 | 6 |  |  |  |  | ● | ●
Hansel | Itinerary generation core engine (AI scheduling) | Sprint 3 | 20 | [6 empty] | ● | ●
Hansel | Crowd data integration + API endpoints | Sprint 3 | 16 | [6 empty] | ● | ●
Hansel | 5 POI/day + geographic proximity algorithm | Sprint 3 | 12 | [6 empty] | ● | ●
Hansel | Integrate ML predictions with backend | Sprint 3 | 12 | [6 empty] | ● | ●
Hansel | AI Planner backend (Gemini + session memory) | Sprint 4 | 16 | [8 empty] | ● | ●
Hansel | EC2 & Vercel setup | Sprint 4 | 12 | [8 empty] | ● | ●
Hansel | Route API integration (Mapbox) | Sprint 4 | 12 | [8 empty] | ● | ●
Hansel | Database setup (PostGIS) | Sprint 4 | 16 | [8 empty] | ● | ●
Hansel | Performance optimization | Sprint 5 | 16 | [10 empty] | ● | ●
Hansel | Final paper writing | Sprint 5 | 40 | [10 empty] | ● | ●
Hansel | Documentation cleanup | Sprint 5 | 12 | [10 empty] | ● | ●
Hansel | Final deployment + monitoring | Sprint 5 | 12 | [10 empty] | ● | ●
Alison
Alison | Crowd data feasibility spike (NYC Open Data) | Sprint 1 | 24 |  |  | ● | ●
Alison | Provide data quality report | Sprint 2 | 16 |  |  |  |  | ● | ●
Alison | Provide preliminary integrated dataset | Sprint 2 | 24 |  |  |  |  | ● | ●
Alison | Finalised busyness formula and result grade | Sprint 3 | 12 | [6 empty] | ● | ●
Alison | ML preparation: Training plan, initial result | Sprint 3 | 20 | [6 empty] | ● | ●
Alison | Evaluate ML model (metrics, validation) | Sprint 3 | 12 | [6 empty] | ● | ●
Alison | Integrate ML predictions with backend | Sprint 3 | 12 | [6 empty] | ● | ●
Alison | Integration testing + bug fixes | Sprint 4 | 24 | [8 empty] | ● | ●
Alison | Final user testing + iterations | Sprint 5 | 24 | [10 empty] | ● | ●
Alison | Final paper writing | Sprint 5 | 40 | [10 empty] | ● | ●
Eoin
Eoin | React-Vite + TypeScript env | Sprint 1 | 12 |  |  | ● | ●
Eoin | Initial frontend structure (no features) | Sprint 1 | 8 |  |  | ● | ●
Eoin | Auth flow UI (Web) | Sprint 2 | 12 |  |  |  |  | ● | ●
Eoin | Bottom navigation component (Web) | Sprint 2 | 8 |  |  |  |  | ● | ●
Eoin | Explore tab UI + Save icon on POI cards (Web) | Sprint 2 | 16 |  |  |  |  | ● | ●
Eoin | POI Detail page UI (Web) | Sprint 2 | 16 |  |  |  |  | ● | ●
Eoin | My Itinerary tab shell + date picker (Web) | Sprint 2 | 8 |  |  |  |  | ● | ●
Eoin | My Itinerary 4-section UI (Web) | Sprint 3 | 20 | [6 empty] | ● | ●
Eoin | Itinerary view page (Web) | Sprint 3 | 16 | [6 empty] | ● | ●
Eoin | "Why this time" UI (Web) | Sprint 3 | 6 | [6 empty] | ● | ●
Eoin | Loading & error states (Web) | Sprint 3 | 6 | [6 empty] | ● | ●
Eoin | In-line Itinerary Editor (Web) | Sprint 3 | 12 | [6 empty] | ● | ●
Eoin | Saved tab functional (Web) | Sprint 4 | 8 | [8 empty] | ● | ●
Eoin | AI Planner UI (Web) | Sprint 4 | 12 | [8 empty] | ● | ●
Eoin | Route display component (Web) | Sprint 4 | 10 | [8 empty] | ● | ●
Eoin | Filter POIs by interest / accessibility | Sprint 5 | 16 | [10 empty] | ● | ●
Eoin | "Surprise Me" entry on Explore | Sprint 5 | 12 | [10 empty] | ● | ●
Eoin | Polish UI + animations | Sprint 5 | 20 | [10 empty] | ● | ●
Eoin | Final paper writing | Sprint 5 | 40 | [10 empty] | ● | ●
Sean
Sean | Mobile env | Sprint 1 | 12 |  |  | ● | ●
Sean | Initial frontend structure (no features) | Sprint 1 | 8 |  |  | ● | ●
Sean | UX strategy (web vs mobile differentiation) | Sprint 1 | 16 |  |  | ● | ●
Sean | Auth flow + Nav (Mobile) | Sprint 2 | 16 |  |  |  |  | ● | ●
Sean | Explore tab + POI Detail (Mobile) | Sprint 2 | 28 |  |  |  |  | ● | ●
Sean | My Itinerary tab shell + date picker (Mobile) | Sprint 2 | 6 |  |  |  |  | ● | ●
Sean | Itinerary view (Mobile) | Sprint 3 | 24 | [6 empty] | ● | ●
Sean | "Why this time" + states (Mobile) | Sprint 3 | 16 | [6 empty] | ● | ●
Sean | My Itinerary 4-section UI (Mobile) | Sprint 3 | 20 | [6 empty] | ● | ●
Sean | In-line Itinerary Editor (Mobile) | Sprint 4 | 6 | [8 empty] | ● | ●
Sean | Route display component (Mobile) | Sprint 4 | 10 | [8 empty] | ● | ●
Sean | Saved tab functional (Mobile) | Sprint 4 | 8 | [8 empty] | ● | ●
Sean | AI Planner UI (Mobile) | Sprint 4 | 12 | [8 empty] | ● | ●
Sean | Filter POIs by interest / accessibility | Sprint 5 | 16 | [10 empty] | ● | ●
Sean | "Surprise Me" entry on Explore | Sprint 5 | 12 | [10 empty] | ● | ●
Sean | Polish UI + animations | Sprint 5 | 20 | [10 empty] | ● | ●
Sean | Final paper writing | Sprint 5 | 40 | [10 empty] | ● | ●
KEY MILESTONES
📌 | Sprint 1 Review (in person) | 5 Jun 2026 |  |  |  |  | ★
📌 | Sprint 2 Review + Presentations 1+2 | 19 Jun 2026 | [6 empty] | ★
📌 | Sprint 3 Review + Presentations 3+4 | 3 Jul 2026 | [8 empty] | ★
📌 | Sprint 4 Review + Presentations 5+6 | 17 Jul 2026 | [10 empty] | ★
📌 | Public Demo | 28 Jul 2026 | [12 empty] | ★
📌 | Viva Interviews | 29–30 Jul 2026 | [12 empty] | ★
📌 | Group Paper + Repo Submission | 7 Aug 2026 | [13 empty] | ★

## Budget
Offpeak — Project Budget
Activity | Budget Base (h) | Planned Hours (Backlog Est.) | Actual Hours (Backlog Real) | Variance (Plan−Actual) | % Used | Buffer 30% (h) | Total Budget (h) | Tools / Services | Actual Cost (€) | Budget Cost (€) | Remaining (€)
1. Requirements & Research | 41 | 44 | 42 | 2 | 95.45% | 12.3 | 53.3 | User interviews, competitor reviews, literature review, POI curation | 840 | 1066 | 226
2. Design (UX/UI) | 50 | 54 | 64 | -10 | 118.5% | 15 | 65 | Figma (Free Plan) | 1280 | 1300 | 20
3. Backend Development | 111 | 130 | 127 | 3 | 97.69% | 33.3 | 144.3 | Firebase Auth, FastAPI, PostGIS (Free Tier) | 2540 | 2886 | 346
4. Web Frontend | 206 | 204 | 204 | 0 | 100% | 61.8 | 267.8 | React-Vite, Vercel (Free Tier) | 4080 | 5356 | 1276
5. Mobile Development | 146 | 160 | 112 | 48 | 70% | 43.8 | 189.8 | React Native / PWA | 2240 | 3796 | 1556
6. ML / Data Engineering | 175 | 190 | 206 | -16 | 108.4% | 52.5 | 227.5 | NYC Open Data, Prophet/Pandas (open source), Gemini API | 4120 | 4550 | 430
7. Integration | 11 | 0 | 0 | 0 | 0% | 3.3 | 14.3 | Mapbox Directions API (Free Tier) | 0 | 286 | 286
8. Testing & QA | 72 | 74 | 74 | 0 | 100% | 21.6 | 93.6 | User testing sessions with target users | 1480 | 1872 | 392
9. Deployment & DevOps | 31 | 34 | 33 | 1 | 97.06% | 9.3 | 40.3 | AWS EC2 (Free Tier), Vercel hosting | 660 | 806 | 146
10. Project Management | 109 | 138 | 136 | 2 | 98.55% | 32.7 | 141.7 | Trello, Google Drive, Slack (free), Overleaf (LaTeX) | 2720 | 2834 | 114
TOTAL | 952 | 1028 | 998 | 30 | 97.08% | 285.6 | 1237.6 |  | 19960 | 24752 | 4792